## 2018 Plan
Feature | Priority from Planning Call | Impact | Type | Source | Priority (from Guangzhou) | Top 4 (from Guangzhou) | Orginal Plan | Release Plan | Current Release Date | Actual Release date | Effort Estimate S < 3 Man-months M < 6 man months L > 6 man months | Comments
RapidsDB Storage Engine |  |  | Performance |  | 1 | top 4
SE v0.3.1 (loader enhancements) | [7 empty] | R3.3.1 | 2018-01-29 |  |  | Enhance Loader to support configruable delimiters, and end-of-line chars.
SE v0.4 (performance) | [7 empty] | R3.4 | 2018-03-18 |  |  | Improve scan and index performance
SE v0.5 (integration with new execution engine) |  | TPC-H, TPC-DS | Performance |  |  |  | R3.3 | R3.5 | 2018-05-01 |  |  | Optimize the interface from the new run-time for accessing SE data
SF 10000 test | [7 empty] | R3.4 | 2018-03-18 |  |  | Feasibility study based on accessing SF10000 lineitem table
Integration with Parallel Loader | [7 empty] | 1 |  |  |  | Need to define integration plan with Parallel Loader
Persist schema metadata, row data | 1 | [5 empty] | R3.4 | R3.7 | 2018-12-18 |  |  | Persist schema and row data to disk and then automatically reload when restarting a cluster
Encryption | [7 empty] | 2 |  |  |  | Could this be first phase of security? Make this user-configurable eg MD5 or custom
Table-level security | [7 empty] | 2 |  |  |  | Dependent on LDAP Authentication
Backup/Restore | [7 empty] | 2 |  |  |  | Support the ability to backup and restore specified set of tables. The user should be able to use the backup to restore the data to SE on another cluster with a different configuration. It would also be highly desirable to be able to use the backup to restore the data to another database. Discussed the approach that this was equivalent to a multi-table export and load.
Other performance (phase 2) | [7 empty] | TBD |  |  |  | Improve join efficieny for queries involving only SE tables: 1) Push down bloom filters 2) Push down list of keys 3) Push down some joins Dependent on results of perf work from v0.5
JDBC Driver | [10 empty] | L
JDBC V3 (Continuous queries) | [6 empty] | R3.3 | R3.7 | 2018-12-18 |  |  | True support for continuous queries as part of the work to support continuous queries in the RDP Engine
Prepared Statements | [7 empty] | R3.4 | 2018-03-18 |  |  | Support JDBC prepareStatetement interface
JDBC-based Connectors
Support CREATE TABLE | [7 empty] | R3.4 | 2018-03-18 |  |  | Add CREATE TABLE support to Oracle, Postgres and JDBC Connectors (already supported in MemSQL Connector)
Hadoop csv Connector
Hadoop csv: Phase 3 (Hive-style partitioning) |  |  | Performance |  |  |  |  | R3.3.1 | 2018-01-29 |  |  | Add support for Hive-style partitioning, to allow for data pruning when there are predicates on the partitioning columns
Hadoop csv: Phase 3 (load ehancements) | [6 empty] | R3.3 | R3.3.1 | 2018-02-28 |  |  | Add new options: TERMINATOR - for specifying how records are terminated ESCAPE - for specifying that fields are using the specified character as an escape character ENCLOSED BY - for specifying the character used for enclosing fields (eg double quote) SEPARATOR -allow the use of a 2 character string as the field separator NOTE: the support for the options described above will likely be integrated with the support for Computed Columns which is a separate feature for this release.
Write interface | [7 empty] | R3.5 | 2018-05-01 |  |  | Need to determine importance of this - could use JDBC Connector with Phoenix JDBC Driver to write data to HBASE, or Impala to write out to other HDFS file formats.
Other file formats (eg. Parquet) |  |  |  | STG3 Plan |  |  |  | TBD |  |  | S | Should understand this with respect to how we handle columnar data. Could be offset by being able to use Impala or Spark SQL to access Parquet.
Hive metadata integration | [7 empty] | TBD
Performance format | [7 empty] | R3.6 |  |  |  | Provide a high-perfomance format that would deliver the best performance for RDP. This could be influenced by the new run-time being delivered in R3.5.
Current plan features:
VIEWS Phase 2 | 1 |  | Competitive | P2 SOW, STG3 Plan |  |  |  | TBD |  |  |  | Support CREATE VIEW
Analytic Windowing | 1? | TPC-DS | Analytics | P2 SOW, STG3 Plan |  |  | R3.4 | R3.6 | 2018-08-01 |  | S | Used by 12 of the TPC-DS queries, and will also provide some windowing capabilities for streams.
Query Caching | 1 | TPC-DS | Performance | P2 SOW, STG3 Plan | 1 | top 4 | R3.2 | R3.5 | 2018-05-01 |  | S | This is important for queries where there are repeated sub-queries, which is commonly seen with the "WITH" clause, so that the sub-query is only evaluated once. Some of the SZSE queries used repeated "WITH" clauses. Also, will be important for R (for iterative processing).
JOIN Order |  | TPC-H, TPC-DS | Performance | P2 SOW, STG3 Plan |  |  | R3.3 | R3.6 | 2018-08-01 |  | S | The peformance of multi-table joins can be signficantly impacted by the ordering of the joins in the final query execution plan. While a sophisticated end-user can provide an optimal odering for the original query, this is can be very difficult for the end-user and should be handled by the query optimizer. To do this requires some form of plan costing in the Optimizer.
Performance:
Execution Engine Performance - Phase 1 |  |  | Performance |  |  |  | R3.3 | R3.5 | 2018-05-01 |  |  | This is a placeholder for work items that will need to be prioritized as a result of the Execution Engine Performance Evaluation being done as part of Release 3.2.
Execution Engine Performance - Phase 2 |  |  | Performance |  |  |  | R3.4 | R3.6 | 2018-08-01 |  |  | This is a placeholder for work items that will need to be prioritized as a result of the Execution Engine Performance Evaluation being done as part of Release 3.2.
Cost-based Optimizer (Phase 1) |  | TPC-H, TPC-DS | Performance |  |  |  | R3.3 | R3.6 | 2018-08-01 |  | M | Goes with Join Order - make general category. Initial support for JOIN ORDER
Multi-column JOINs |  |  | Performance |  |  |  | R3.3 | TBD |  |  | S | This was an issue for some of the SZSE queries
Dynamic repartitioning |  |  | Performance |  |  |  |  | TBD |  |  | S | For JDBC Connectors and the Hadoop csv Connector, for pull-up queries we currently pull-up the data through a single connection to one node, which is a potential performance or memory issue . Typically this would occur when doing heterogeneous joins. This work would dynamically redistribute the data over DQE nodes.
Move major data structures off-heap | 1? | TPC-DS (for SE) | Performance | P2 SOW, HARDENING |  |  |  | R3.5 | 2018-05-01 |  | S | There were two items driving this feature: 1. Moving the table data off-heap. This was an issue with VoltDB because any table data extracted from VoltDB had to be stored completely in a temp table before the data could be processed. Due to the limitations of join processing in VoltDB, we often had to pull-up the data from VoltDB into these temporary tables. This is not an issue with RapidsSE because the RapidsSE data store is already off-heap. This is also not an issue for MemSQL or the Hadoop csv Connectors because they are able to stream the data one row at a time time, and do not have to materialize the complete table. 2. Intermediate hash maps - we create hash maps when doing join processing, and these maps can end up being large when we are joining a very large number of rows. The hash maps are implemented as standard Java hash maps which are not memory efficient and have a limit of 2B entries, which will be a problem for queries on SF1000. We need to have a more efficient hash map which has no memory limitations We need to assess the impact of this now that we have MemSQL and RapidsSE.
Improve INSERT … SELECT performance for JDBC Connectors |  |  | Performance |  |  |  |  | R3.4 | 2018-03-18 |  | S | The current implementation does the row inserts one row at a time. Performance can be improved signficantly by specifying multiple VALUES clauses in a single INSERT statement. The expectation is that the result sets will not be that large and so this may not be a major issue - need to assess importance of this.
Streaming: |  |  | Competitive
Kafka Connector Phase 1 | [6 empty] | R3.2 | TBD |  |  |  | The Kafka Connector will support bi-directional access to Kafka allowing data to be queried from Kafka as well as allowing data to be inserted back into Kafka. In Kafka the basic categorizing tool is a "topic." It is basically a named stream of events. A Kafka topic corresponds to a table/stream in RapidsDB. With the RapidsDB Kafka Connector the user would be able to access a topic as shown below: CREATE CONNECTOR kafka TYPE kafka WITH host = <Kafka ip address>, port=<Kakfa port>, NODE …. SELECT * from kafka.mytopic. The data returned will be 3 columns: KEY, VALUE, TS. The user application will be responsible for interpreting the KEY and VALUE columns, The TS column will be the timestamp for that entry.
Kafka Connector Phase 2 | 1 |  | Competitive |  |  |  | R3.3 | R3.7 | 2018-12-18 |  |  | In Phase 2, the user will be able to associate a schema definition with the Kafka VALUE field which will allow the user to query the data contained in the VALUE field as though the VALUE field was a row from a SQL table. For example, if the VALUE field is in csv format, the user will be able to associate a column name with each of the csv fields. This will be equivalent to the current support provided in the Hadoop csv Connector when accessing Hadoop csv files. The plan is to take advantage of the support planned for Computed Columns (described as a separate feature). For the Kafka Connector this means that it will be possible to create computed columns from the VALUE column by applying functions to the VALUE column to extract the data for a set of computed columns. For example: if the VALUE field for the Kafka topic "mytopic" was in csv format with 3 fields, it will be possible the specify three computed columns ORDER_NO, ITEM_NO and CUSTOMER, then the user would be able to issue the following query: Select * from mytopic where CUSTOMER = ‘18997434’ The functions to be supported (e.g. csv) for generating the computed columns is TBD
Computed columns |  |  | Competitive |  |  |  | R3.3 | R3.7 | 2018-12-18 |  |  | A computed column is computed from an expression that can use other columns in the same table. For example, if a column in a table was in csv format, the user will be able to associate a column name with each of the csv fields. This capability will be used by the Kafka Connector to create computed columns from the VALUE column by applying functions to the VALUE column to extract the data for a set of computed columns. The exact syntax for specifying the computed columns is TBD. The user can refer to the SQL Server, and MemSQL documentation for examples of computed columns. For example: if the VALUE field for the Kafka topic "mytopic" was in csv format with 3 fields, it will be possible the specify three computed columns ORDER_NO, ITEM_NO and CUSTOMER, then the user would be able to issue the following query: Select * from mytopic where CUSTOMER = ‘18997434’ The functions to be supported (e.g. csv) for generating the computed columns is TBD Computed columns are also expected to play an important role for handling the complex results returned from ML algorithms.
Joining two streams |  |  | Competitive | [7 empty] | S
continuous queries | 1 |  | Competitive |  |  |  | R3.3 | R3.7 | 2018-12-18 |  | S | Removes the micro-batching approach we currently use where we terminate a query on a fixed time window boundary and then have the rapids-shell resubmit the query. This is the case where the query is reading an indefinite monotonic stream and the query is able to emit result rows as the query progresses (because the stream is monotonically ordered). A simple example is where the query is aggregating on a monotonic timestamp key. When the monotonic key changes then the aggregate operator (say) can emit its computation because the monotonic key has changed and will never be seen again (assuming no out of sequence arrival). The query never ends but can emit rows when the grouping expression (over a monotonic key) changes.
exactly once (implies use of Kafka) | 2 |  | Competitive |  |  |  |  | TBD |  |  | M | Needed to have Enterprise-grade streaming so that messages are not lost or processed twice. Does this also imply that we have to be able to restart a query? This needs to be scoped.
progessive queries |  |  | Competitive |  |  |  |  | TBD |  |  | S | This is the case where continuous output can be produced in the absence of input.. Requires making various judgements/decisions as to what are these boundaries, under what conditions (time or some other expression/computation) are the markers put into the row pipelines and who injects them.
sliding, jumping | [7 empty] | R3.6 | 2018-08-01 |  | S | Allow more complex windowing support for streams, for example: SELECT ts, MAX(temp) OVER( ORDER BY ts RANGE INTERVAL 1 HOUR PRECEDING ) FROM events;
recovery from failures |  |  | Enterprise | STG3 Plan |  |  |  | TBD |  |  | See HA
HA |  |  | Enterprise | STG3 Plan |  |  |  | TBD |  |  | See HA
Machine Learning/R |  |  | Competitive | STG3 Plan (Machine Learning)
Phase 2: R support - foundation work (incl. basic algorithms) | [7 empty] | TBD |  |  | M | Develop Client R interface (based on H2O client) Develop Rapids R DataFrame R Library support (modelled after H2O) Support for User-defined types (for returning complex results) Support for User-defined functions (for invoking R functions) Support for iterative calculations Support for query caching (for performance of iterative operations against same datasets) Parallelized algorithms (eg GLM, Clustering)
Phase 2: more advanced algorithms | [7 empty] | TBD |  |  | M | Need to prioritize based on feedback from customers such as the Census Bureau
Import of external models (eg via PMML) | [7 empty] | TBD |  |  | M
High order analytics | [7 empty] | TBD |  |  | M | How to perform the high order analytics efficiently. For example, will we need columnar data?
Execute/deploy existing model | [7 empty] | 1 |  |  |  | Dependent on UDF, UDT support. Need to confirm if UDF/UDT support is sufficient
UDF/UDT Support |  |  | Competitive |  |  |  |  | R3.6 | 2018-08-01 |  |  | Support UDFs and UDTs written in Java
Benchmarks (TPC-H SF1000, TPC-DS SF1000) | 1 |  | Competitive | STG3 Plan |  |  |  | R3.6 | 2018-08-01 |  | M | Support running TPC-H SF1000 on MemSQL and SE. For SE this must wait for the completion of the R3.5 release. One known area of concern is join ordering, which will not be addressed in R3.5, and so we will still need to manually set the join order for some of the queries. TPC-DS: For SE this must wait for the R3.5 release, and at that point we can run 80% of the TPC-DS queries. We need support for Analytic Windowing and ROLLUP to run remaining 20% of queries. Will still have issues with join order for some of the queries.
Unified DML support |  |  | Competitive | STG3 Plan
DELETE | 1 | [6 empty] | TBD
UPDATE | [7 empty] | TBD |  |  | S
CREATE AS SELECT | [7 empty] | R3.4 | 2018-03-18 |  |  | Automatically creates a table based on the columns in the result set and then inserts the result set into the table
TRUNCATE | [7 empty] | R3.5 | 2018-05-01
Enterprise:
HA - loss of a node |  |  | Enterprise | [7 empty] | L
- Phase 1: Restart query in flight | [7 empty] | 3
- Phase 2 - Recover query in flight | [7 empty] | 3
- Add node back | [7 empty] | 3
HA - disaster recovery |  |  | Enterprise | STG3 Plan |  |  |  | 3 |  |  | L
Dynamic cluster mangement - Phase 1 |  |  | Enterprise |  |  |  | R3.4 | 3 |  |  | M | Add and remove nodes from quiesced RapidsDB Cluster (does not include RapidsSE)
Security - use of G/R security model | 2 |  | Enterprise | [7 empty] | M
Phase 1: user-level authentication | [7 empty] | R3.5 | 2018-05-01 |  |  | Provide user-level authentication to control access to the system via rapids-shell or JDBC. Initially support LDAP. Likely to be moved to R3.6
Phase 2: table-level security | [7 empty] | 2 |  |  |  | Investigate feasibility of quick-fix for some level of table-level security.
encryption | [7 empty] | 2
Resource Management |  |  | Enterprise | HARDENING | [6 empty] | L
Resource Management framework | [6 empty] | R3.2 | R3.5 | 2018-05-01 |  |  | We currently have no effective way of limiting the use of system resources, such as file descriptors or memory. This can lead to resource exhaustion, which can cause the DQS to fail. The only mechanism we have today to control this is by limiting the number of concurrent queries that the system will attempt to execute, but even this can fail when pulling up large amounts of data into the Rapids Execution Engine (eg when joining across Connectors). We need to have a way to estimate the memory usage for a query and then do resource-based query scheduling.
CPU management | [7 empty] | TBD
efficient memory usage | [6 empty] | R3.3 | R3.5 | 2018-05-01 |  | S | Intermediate hash maps - we create hash maps when doing join processing, and these maps can end up being large when we are joining a very large number of rows. The hash maps are implemented as standard Java hash maps which are not memory efficient and have a limit of 2B entries, which will be a problem for queries on SF1000. We need to have a more efficient hash map which has no memory limitations. We need to assess the impact of this now that we have MemSQL and RapidsSE.
overflow to disk |  |  |  | STG3 Plan |  |  |  | TBD |  |  | M
Multi-tenancy (SE) | 2 |  | Enterprise | STG3 Plan |  |  |  | TBD |  |  | M | Related to security
Heterogenous transaction management |  |  | Enterprise | [7 empty] | L
Usability
Query tracking | 2 |  | Enterprise |  |  |  | R3.4 | TBD |  |  | S
Will be important for streams in order to see what is going on. Implies getting improved metrics out of the system.
Query hold/continue/cancel | 2 |  | Enterprise |  |  |  | R3.4 | TBD |  |  | S
Query prioritization | 2 |  | Competitive |  |  |  |  | TBD |  |  | S
Metadata Management | [11 empty] | Deal with the issue where there are 10's thousands of tables/views in the target system
Updatable list of tables | [7 empty] | R3.4 | 2018-03-18 |  |  | This is viewed as a short-term approach to allow the user to specify a list of tables to be accessed, and then provide a way to update the list of tables without having to drop and recreate the connector.
Lazy metadata retrieval | [7 empty] | TBD |  |  |  | THIS NEEDS TO BE REVIEWED Provide an option where the Connector only retrieves the list of tables available, but there is no column metadata retrieved. I think that it should be a reasonably quick (to be proven) operation to retrieve the list of tables, even when you have 300,000 tables as is the case with the current POC. We would need to make certain that the data structure used by the Connector can be efficiently searched when doing the table lookup. The Planner would now need to change because it is possible that we do not have the column metadata for a table, and so the first pass of the Planner would be to generate a list of the tables referenced in the query and send that list to all of the Connectors. For all of the tables that a Connector has an entry for, if the column metadata is missing then the metadata would be retrieved at that time, and the Connector would respond to the Planner once all of the column metadata had been retrieved.
rapids-shell V2
rapids-shell V2: Phase 1 - Using RDP JDBC Driver | [7 empty] | R3.4 | 2018-03-18 |  |  | Can be released independently of RDP release
rapids-shell V2: Phase 2 - Using Proxy JDBC Driver | [7 empty] | TBD |  |  |  | Can be released independently of RDP release
TPC-DS
Analytic Windowing (see Analytic Windowing above) | [6 empty] | R3.4 | R3.6 | 2018-08-01
FULL OUTER JOIN | [7 empty] | R3.5 | 2018-05-01
ROLLUP | [7 empty] | R3.6 | 2018-08-01
OLAP
GROUPING SETS, CUBE | [7 empty] | TBD |  |  |  | With GROUPING SETS, CUBE and ROLLUP we would have the equivalent ROLAP support to Postgres. Here is an article on the Postgres support added in 9.5: https://www.depesz.com/2015/05/24/waiting-for-9-5-support-grouping-sets-cube-and-rollup/
Licensing | [7 empty] | 1 |  |  |  | Need to agree on requirements. Suggested approach is to provide a hook in the bootstrapper so that the licensing code can be called during install and start to validate license.

## 2017 Plan
Feature | Priority from Planning Call | Impact | Type | Source | Priority (from Guangzhou) | Top 4 (from Guangzhou) | Orginal Plan | Currrent Plan (per Dev Plan rev 16) | Current target release date (per Dev Plan rev 16) | Revised release plan | Revised target release date | Actual Release date | Effort Estimate S < 3 Man-months M < 6 man months L > 6 man months | Comments
RapidsDB Storage Engine |  |  | Performance |  | 1 | top 4
SE v0.1 (single node, no indexes) | 1 | [5 empty] | R3.0 Beta | R3.0 Beta | 2016-11-30 |  |  | 2016-12-17 | M
SE v0.2 (multiple nodes, no indexes) | 1 | [5 empty] | R3.1 | R3.1 | 2017-03-31 |  |  | 2017-05-15 | M
SE v0.3 (multiple nodes, indexes, range queries) | 1 | TPC-H, TPC-DS | Performance |  |  |  | R3.2 | R3.3 | 2017-08-31 | R3.3 | 2017-11-20 | 2018-11-22 | M
SE v0.3.1 (loader enhancements) | [9 empty] | R3.3.1 | 2018-01-29 |  |  | Enhance Loader to support configruable delimiters, and end-of-line chars.
SE v0.4 (more efficient join processing, loader enhancements, schema metadata persistence) |  | TPC-H, TPC-DS | Performance |  |  |  | R3.3 | R3.4 | 2017-12-17 |  |  |  |  | Improve join efficieny for queries involving only SE tables: 1) Push down bloom filters 2) Push down list of keys 3) Push down some joins Persist schema metadata
SE v0.4 (Persist schema metadata, row data) | 1 | [5 empty] | R3.4 |  |  | R3.5 | 2018-05-01
SF 10000 test | [9 empty] | R3.4 | 2018-02-28 |  |  | To start after completion of R3.3
JDBC Driver | [12 empty] | L
JDBC V1 | 1 |  | Competitive |  | 1 | top 4 | R3.0 GA | R3.0 GA | 2016-12-31 |  |  | 2017-02-17
JDBC V2 (Connection Balancing, setMaxRows()) | [6 empty] | R3.1 | R3.1 | 2017-03-31 |  |  | 2017-05-15
JDBC V3 (Continuous queries) | [6 empty] | R3.3 |  |  | R3.4 | 2018-02-28 |  |  | Add support for streaming queries, which are equivalent to the "continuous queries" supported from the rapids-shell
Prepared Statements | [9 empty] | R3.4 | 2018-02-28 |  |  | Support JDBC prepareStatetement interface
JDBC Connector - other data sources (beyond MemSQL) | 1 |  | Competitive |  | 1 |  | R3.2 | R3.2 | 2017-06-30 | R3.3 | 2017-11-20 |  | S | a. Case-insensitive naming b. Certify the JDBC Connector against Postgres/Greenplum and Oracle (as discussed in item 1 above). Certification of other databases, such as DB2 and Hive would come later c. Optimize the metadata retrieval when the TABLE clause is used (see item 2). verifying that the customization features are sufficient.
Hadoop csv Connector
Hadoop csv: Phase 1 (multi-node, partitioned) | [6 empty] | R3.0 GA | R3.0 GA | 2016-12-31 |  |  | 2017-02-17
Hadoop csv: Phase 2 (support for multiple files and dynamically adding files) | [6 empty] | R3.2 | R3.2 | 2017-06-30 | R3.3 | 2017-11-20 | 2018-11-22 |  | 1) Support the ability to include wildcard characters for the file name to allow multiple files to be associated with a single table 2) Support the ability to include new csv files to be accessed without requiring the user to drop and recreate the Connector with new files to be accessed
Hadoop csv: Phase 3 (Hive-style partitioning) |  |  | Performance | [6 empty] | R3.3.1 | 2018-01-29 |  |  | Add support for Hive-style partitioning, to allow for data pruning when there are predicates on the partitioning columns
Hadoop csv: Phase 3 (load ehancements) | [6 empty] | R3.3 | R3.3 | 2017-08-31 | R3.3.1 | 2018-02-28 |  |  | Add new options: TERMINATOR - for specifying how records are terminated ESCAPE - for specifying that fields are using the specified character as an escape character ENCLOSED BY - for specifying the character used for enclosing fields (eg double quote) SEPARATOR -allow the use of a 2 character string as the field separator NOTE: the support for the options described above will likely be integrated with the support for Computed Columns which is a separate feature for this release.
Hadoop csv: Phase 6 (Write interface) | [9 empty] | TBD |  |  |  | Need to determine importance of this - could use JDBC Connector with Phoenix JDBC Driver to write data to HBASE, or Impala to write out to other HDFS file formats.
Hadoop csv: Phase 4 (other file formats (eg. Parquet)) |  |  |  | STG3 Plan | [5 empty] | TBD |  |  | S | Should understand this with respect to how we handle columnar data. Could be offset by being able to use Impala or Spark SQL to access Parquet.
Hadoop csv: Phase 5 (Hive metadata integration) | [9 empty] | TBD
Current plan features:
WITH | 1 | TPC-H, TPC-DS | Competitive | P2 SOW, STG3 Plan |  |  | R3.1 | R3.1 | 2017-03-31 |  |  | 2017-05-15 | S | WITH is commonly used with complex queries as a way to both simplify the final query and to build common table expressions. Many of the TPC-DS queries use WITH
VIEWS Phase 1 | 1 |  | Competitive | P2 SOW, STG3 Plan | [5 empty] | R3.3 | 2017-11-20 | 2018-11-22 | S | The MemSQL and Generic JDBC Connectors will include VIEWs as part of the metadata for the associated data source. A VIEW will appear exactly the same as a TABLE in the RapidsDB Metadata and can be queried as though it was a table. There will be no support for CREATE VIEW from RapidsDB as part of this feature.
VIEWS Phase 2 | 1 |  | Competitive | P2 SOW, STG3 Plan | [9 empty] | Support CREATE VIEW
Analytic Windowing | 1? | TPC-DS | Analytics | P2 SOW, STG3 Plan |  |  | R3.4 | R3.4 | 2017-12-17 | R3.6 | 2018-08-01 |  | S | Used by 12 of the TPC-DS queries, and will also provide some windowing capabilities for streams.
Query Caching | 1 | TPC-DS | Performance | P2 SOW, STG3 Plan | 1 | top 4 | R3.2 | R3.3 | 2017-08-31 | R3.5 | 2018-05-01 |  | S | This is important for queries where there are repeated sub-queries, which is commonly seen with the "WITH" clause, so that the sub-query is only evaluated once. Some of the SZSE queries used repeated "WITH" clauses. Also, will be important for R (for iterative processing).
JOIN Order |  | TPC-H, TPC-DS | Performance | P2 SOW, STG3 Plan |  |  | R3.3 | R3.4 | 2017-12-17 | R3.6 | TBD |  | S | The peformance of multi-table joins can be signficantly impacted by the ordering of the joins in the final query execution plan. While a sophisticated end-user can provide an optimal odering for the original query, this is can be very difficult for the end-user and should be handled by the query optimizer. To do this requires some form of plan costing in the Optimizer.
DQC Role support | 1 |  | Performance |  | 1 |  |  | R3.1 | 2017-03-31 |  |  |  |  | Distribute concurrent query workload over multiple DQC nodes. This will be handled via the Connection Balancing feature being delivered with JDBC V2
Performance:
Execution Engine Peformance Evaluation |  |  | Performance |  |  |  | R3.2 | R3.2 | 2017-06-30 |  |  | 2017-06-30 |  | As we move forward with the development of RapidsSE as our own internal storage engine, we need to determine if the performance of the existing Java-based Execution Engine can be improved sufficiently so that we can compete with other in-memory query engines such as MemSQL and Impala. Some improvements have been already identified such as more efficient hash maps and query caching. The goal of this evaluation is to determine whether even with all of these improvements, can we still achieve the desired level of performance, and if not, what steps should be taken to achieve the desired level of performance? The results of this evaluation could impact the future work planned in this and the following releases and so placeholders have been added to the Release 3.3 and Release 3.4 for possible work in this area.
Execution Engine Performance - Phase 1 |  |  | Performance |  |  |  | R3.3 | R3.3 | 2017-08-31 | R3.5 | 2018-05-01 |  |  | This is a placeholder for work items that will need to be prioritized as a result of the Execution Engine Performance Evaluation being done as part of Release 3.2.
Execution Engine Performance - Phase 2 |  |  | Performance |  |  |  | R3.4 | R3.4 | 2017-12-17 | R3.6 | 2018-08-01 |  |  | This is a placeholder for work items that will need to be prioritized as a result of the Execution Engine Performance Evaluation being done as part of Release 3.2.
Cost-based Optimizer (Phase 1) |  | TPC-H, TPC-DS | Performance |  |  |  | R3.3 | R3.4 | 2017-12-17 | R3.6 | 2018-08-01 |  | M | Goes with Join Order - make general category. Initial support for JOIN ORDER
Multi-column JOINs |  |  | Performance |  |  |  | R3.3 | R3.4 | 2017-12-17 | TBD | TBD |  | S | This was an issue for some of the SZSE queries
Dynamic repartitioning |  |  | Performance | [6 empty] | TBD | TBD |  | S | For JDBC Connectors and the Hadoop csv Connector, for pull-up queries we currently pull-up the data through a single connection to one node, which is a potential performance or memory issue . Typically this would occur when doing heterogeneous joins. This work would dynamically redistribute the data over DQE nodes.
Move major data structures off-heap | 1? | TPC-DS (for SE) | Performance | P2 SOW, HARDENING |  |  |  | R3.3 | 2017-08-31 | R3.5 | 2018-05-01 |  | S | There were two items driving this feature: 1. Moving the table data off-heap. This was an issue with VoltDB because any table data extracted from VoltDB had to be stored completely in a temp table before the data could be processed. Due to the limitations of join processing in VoltDB, we often had to pull-up the data from VoltDB into these temporary tables. This is not an issue with RapidsSE because the RapidsSE data store is already off-heap. This is also not an issue for MemSQL or the Hadoop csv Connectors because they are able to stream the data one row at a time time, and do not have to materialize the complete table. 2. Intermediate hash maps - we create hash maps when doing join processing, and these maps can end up being large when we are joining a very large number of rows. The hash maps are implemented as standard Java hash maps which are not memory efficient and have a limit of 2B entries, which will be a problem for queries on SF1000. We need to have a more efficient hash map which has no memory limitations We need to assess the impact of this now that we have MemSQL and RapidsSE.
Improve INSERT … SELECT performance for JDBC Connectors |  |  | Performance | [6 empty] | R3.4 | 2018-02-28 |  | S | The current implementation does the row inserts one row at a time. Performance can be improved signficantly by specifying multiple VALUES clauses in a single INSERT statement. The expectation is that the result sets will not be that large and so this may not be a major issue - need to assess importance of this.
Streaming: |  |  | Competitive
Kafka Connector Phase 1 | [6 empty] | R3.2 | [6 empty] | The Kafka Connector will support bi-directional access to Kafka allowing data to be queried from Kafka as well as allowing data to be inserted back into Kafka. In Kafka the basic categorizing tool is a "topic." It is basically a named stream of events. A Kafka topic corresponds to a table/stream in RapidsDB. With the RapidsDB Kafka Connector the user would be able to access a topic as shown below: CREATE CONNECTOR kafka TYPE kafka WITH host = <Kafka ip address>, port=<Kakfa port>, NODE …. SELECT * from kafka.mytopic. The data returned will be 3 columns: KEY, VALUE, TS. The user application will be responsible for interpreting the KEY and VALUE columns, The TS column will be the timestamp for that entry.
Kafka Connector Phase 2 | 1 |  | Competitive |  |  |  | R3.3 |  |  | TBD | TBD |  |  | In Phase 2, the user will be able to associate a schema definition with the Kafka VALUE field which will allow the user to query the data contained in the VALUE field as though the VALUE field was a row from a SQL table. For example, if the VALUE field is in csv format, the user will be able to associate a column name with each of the csv fields. This will be equivalent to the current support provided in the Hadoop csv Connector when accessing Hadoop csv files. The plan is to take advantage of the support planned for Computed Columns (described as a separate feature). For the Kafka Connector this means that it will be possible to create computed columns from the VALUE column by applying functions to the VALUE column to extract the data for a set of computed columns. For example: if the VALUE field for the Kafka topic "mytopic" was in csv format with 3 fields, it will be possible the specify three computed columns ORDER_NO, ITEM_NO and CUSTOMER, then the user would be able to issue the following query: Select * from mytopic where CUSTOMER = ‘18997434’ The functions to be supported (e.g. csv) for generating the computed columns is TBD
Joining two streams |  |  | Competitive | [9 empty] | S
continuous queries | 1 |  | Competitive |  |  |  | R3.3 |  |  | TBD | TBD |  | S | Removes the micro-batching approach we currently use where we terminate a query on a fixed time window boundary and then have the rapids-shell resubmit the query. This is the case where the query is reading an indefinite monotonic stream and the query is able to emit result rows as the query progresses (because the stream is monotonically ordered). A simple example is where the query is aggregating on a monotonic timestamp key. When the monotonic key changes then the aggregate operator (say) can emit its computation because the monotonic key has changed and will never be seen again (assuming no out of sequence arrival). The query never ends but can emit rows when the grouping expression (over a monotonic key) changes.
exactly once (implies use of Kafka) | 2 |  | Competitive | [6 empty] | TBD | TBD |  | M | Needed to have Enterprise-grade streaming so that messages are not lost or processed twice. Does this also imply that we have to be able to restart a query? This needs to be scoped.
progessive queries |  |  | Competitive | [6 empty] | TBD | TBD |  | S | This is the case where continuous output can be produced in the absence of input.. Requires making various judgements/decisions as to what are these boundaries, under what conditions (time or some other expression/computation) are the markers put into the row pipelines and who injects them.
sliding, jumping | [9 empty] | TBD | TBD |  | S | Allow more complex windowing support for streams, for example: SELECT ts, MAX(temp) OVER( ORDER BY ts RANGE INTERVAL 1 HOUR PRECEDING ) FROM events;
recovery from failures |  |  | Enterprise | STG3 Plan | [8 empty] | See HA
HA |  |  | Enterprise | STG3 Plan | [8 empty] | See HA
Machine Learning/R |  |  | Competitive | STG3 Plan (Machine Learning)
Phase 2: R support - foundation work (incl. basic algorithms) | [12 empty] | M | Develop Client R interface (based on H2O client) Develop Rapids R DataFrame R Library support (modelled after H2O) Support for User-defined types (for returning complex results) Support for User-defined functions (for invoking R functions) Support for iterative calculations Support for query caching (for performance of iterative operations against same datasets) Parallelized algorithms (eg GLM, Clustering)
Phase 2: more advanced algorithms | [12 empty] | M | Need to prioritize based on feedback from customers such as the Census Bureau
Import of external models (eg via PMML) | [12 empty] | M
Computed columns |  |  | Competitive |  |  |  | R3.3 | [6 empty] | A computed column is computed from an expression that can use other columns in the same table. For example, if a column in a table was in csv format, the user will be able to associate a column name with each of the csv fields. This capability will be used by the Kafka Connector to create computed columns from the VALUE column by applying functions to the VALUE column to extract the data for a set of computed columns. The exact syntax for specifying the computed columns is TBD. The user can refer to the SQL Server, and MemSQL documentation for examples of computed columns. For example: if the VALUE field for the Kafka topic "mytopic" was in csv format with 3 fields, it will be possible the specify three computed columns ORDER_NO, ITEM_NO and CUSTOMER, then the user would be able to issue the following query: Select * from mytopic where CUSTOMER = ‘18997434’ The functions to be supported (e.g. csv) for generating the computed columns is TBD Computed columns are also expected to play an important role for handling the complex results returned from ML algorithms.
High order analytics | [12 empty] | M | How to perform the high order analytics efficiently. For example, will we need columnar data?
UDF/UDT Support |  |  | Competitive |  |  |  |  | R3.4 | 2017-12-17 | R3.6 | 2018-08-01
RapidsDB API | 1 |  | Competitive | STG3 Plan | 1 | top 4
Thrift-based message API (wire-line protocol) | 1 | [5 empty] | R3.0 GA | R3.0 GA | 2016-12-31 |  |  | 2017-02-17 |  | Developed as part of the JDBC project. We will document the Thrift-based API, and then other interfaces could be built on top of this API by third parties or the Field team
Benchmarks (TPC-H SF1000, TPC-DS SF1000) | 1 |  | Competitive | STG3 Plan | [8 empty] | M | Support running TPC-H SF1000 on MemSQL and SE. Support running 80% of TPC-DS SF1000 on MemSQL and SE.
Unified DML support |  |  | Competitive | STG3 Plan
standard DML (condenser maps DML to data source) | 1 | [5 empty] | R3.0 Beta | R3.0 Beta | 2016-11-30 |  |  | 2016-12-17 |  | Not transactional. CREATE/DROP TABLE, INSERT, INSERT … SELECT
DELETE | 1
UPDATE | [12 empty] | S
Enterprise:
HA - loss of a node |  |  | Enterprise | [9 empty] | L
- Phase 1: Restart query in flight
- Phase 2 - Recover query in flight
- Add node back
HA - disaster recovery |  |  | Enterprise | STG3 Plan | [8 empty] | L
Dynamic cluster mangement - Phase 1 |  |  | Enterprise |  |  |  | R3.4 | [5 empty] | M | Add and remove nodes from quiesced RapidsDB Cluster (does not include RapidsSE)
Security - use of G/R security model | 2 |  | Enterprise | [9 empty] | M
Phase 1: user-level authentication | [9 empty] | R3.5 | 2018-05-01 |  |  | Provide user-level authentication to control access to the system via rapids-shell or JDBC. Initially support LDAP.
Phase 2: table-level security for SE | [9 empty] | R3.6 | 2018-08-01 |  |  | Possibly do user-level security against multi-tenants
requires use of session mangement
encryption
Resource Management |  |  | Enterprise | HARDENING | [8 empty] | L
Resource Management framework | [6 empty] | R3.2 | R3.3 | 2017-08-31 | R3.5 | 2018-05-01 |  |  | We currently have no effective way of limiting the use of system resources, such as file descriptors or memory. This can lead to resource exhaustion, which can cause the DQS to fail. The only mechanism we have today to control this is by limiting the number of concurrent queries that the system will attempt to execute, but even this can fail when pulling up large amounts of data into the Rapids Execution Engine (eg when joining across Connectors). We need to have a way to estimate the memory usage for a query and then do resource-based query scheduling.
CPU management
efficient memory usage | [6 empty] | R3.3 | R3.3 | 2017-08-31 | R3.5 | 2018-05-01 |  | S | Intermediate hash maps - we create hash maps when doing join processing, and these maps can end up being large when we are joining a very large number of rows. The hash maps are implemented as standard Java hash maps which are not memory efficient and have a limit of 2B entries, which will be a problem for queries on SF1000. We need to have a more efficient hash map which has no memory limitations. We need to assess the impact of this now that we have MemSQL and RapidsSE.
overflow to disk |  |  |  | STG3 Plan | [8 empty] | M
Multi-tenancy (SE) | 2 |  | Enterprise | STG3 Plan | [5 empty] | TBD |  |  | M | Related to security
Initial support provided in RapidsSE.
Heterogenous transaction management |  |  | Enterprise | [9 empty] | L
Usability
Query tracking | 2 |  | Enterprise |  |  |  | R3.4 | R3.4 | 2017-12-17 | TBD |  |  | S
Will be important for streams in order to see what is going on. Implies getting improved metrics out of the system.
Query hold/continue/cancel | 2 |  | Enterprise |  |  |  | R3.4 | R3.4 | 2017-12-17 | TBD |  |  | S
Query prioritization | 2 |  | Competitive | [9 empty] | S
Metadata Management
Index Metadata | [6 empty] | R3.2 | R3.3 | 2017-08-31 | R3.3 | 2017-11-20 | 2018-11-22 |  | With the introduction of indexes in RapisdSE v0.3, we will need to extend the RapidsDB system metadata to also include information about the indexes defined on a table. As part of this work we will extend the Connector interface so that Connectors can return information about indexes if they are supported by the underlying data store, such as MemSQL. This index information can then be used by the RapidsDB Planner when building a query plan, although we have committed plans for enhancing the RapidsDB Planner at this time.
Lazy metadata retrieval | [9 empty] | R3.5 | 2018-05-01 |  |  | Provide an option where the Connector only retrieves the list of tables available, but there is no column metadata retrieved. I think that it should be a reasonably quick (to be proven) operation to retrieve the list of tables, even when you have 300,000 tables as is the case with the current POC. We would need to make certain that the data structure used by the Connector can be efficiently searched when doing the table lookup. The Planner would now need to change because it is possible that we do not have the column metadata for a table, and so the first pass of the Planner would be to generate a list of the tables referenced in the query and send that list to all of the Connectors. For all of the tables that a Connector has an entry for, if the column metadata is missing then the metadata would be retrieved at that time, and the Connector would respond to the Planner once all of the column metadata had been retrieved.
rapids-shell V2
rapids-shell V2: Phase 1 - Using RDP JDBC Driver | [7 empty] | R3.3 | 2017-08-31 | R3.4 | 2018-02-28 |  |  | Can be released independently of RDP release
rapids-shell V2: Phase 2 - Using Proxy JDBC Driver | [9 empty] | TBD | TBD |  |  | Can be released independently of RDP release
TPC-DS
Analytic Windowing (see Analytic Windowing above) | [6 empty] | R3.4 | R3.4 | 2017-12-17 | R3.6 | TBD
FULL OUTER JOIN | [9 empty] | R3.5 | 2018-05-01
ROLLUP | [9 empty] | R3.6 | 2018-08-01
GROUPING SETS, CUBE | [9 empty] | TBD | TBD |  |  | With GROUPING SETS, CUBE and ROLLUP we would have the equivalent ROLAP support to Postgres. Here is an article on the Postgres support added in 9.5: https://www.depesz.com/2015/05/24/waiting-for-9-5-support-grouping-sets-cube-and-rollup/
Other
CREATE AS SELECT | [9 empty] | R3.4 | 2018-02-28 |  |  | Automatically creates a table based on the columns in the result set and then inserts the result set into the table
Licensing | [9 empty] | TBD |  |  |  | Need to agree on requirements. Currently in as a placeholder

## Field Projects
Feature | Current target release date | Actual Release date | Effort Estimate S < 3 Man-months M < 6 man months L > 6 man months | Comments
EXPORT to Kafka | 2017-01-31 |  | S | Provide a way to export data from RapidsDB to Kafka which then allows that data to be used for a variety of purposes eg. loading into a cube to be accessed by BI tools. An initial implemenation could be done by taking advantage of the rapids-shell INTO <pipe> SELECT ..., feature and then having a program that can write from the <pipe> to Kafka. The longer-term solution is to implement the Kafaka Connector mentioned above.
Proxy JDBC Driver
Machine Learning/R
Phase 1: Adopt H2O R
Rapids Manager
ELT |  |  |  | This should be driven from the field and then any work items in the core engine can be identified and scheduled. This should include the parallel loader. It is expected that query tracking and query prioritization will be part of this.
Parallel Loader

## SOW-Hardening Reconciliation
Feature | Planned Release | Actual Release | Comments | Description
Remove VoltDB Network Limit | R2.1 | R2.1
Improve Hash Joins to share data at node level | R2.1 | R2.1
Move data off-heap | R2.1 |  | Deferred | PERFORMANCE: There were two items driving this feature: 1. Moving the table data off-heap. This was an issue with VoltDB because any table data extracted from VoltDB had to be stored completely in a temp table before the data could be processed. Due to the limitations of join processing in VoltDB, we often had to pull-up the data from VoltDB into these temporary tables. This is not an issue with RapidsSE because the RapidsSE data store is already off-heap. This is also not an issue for MemSQL or the Hadoop csv Connectors because they are able to stream the data one row at a time time, and do not have to materialize the complete table. 2. Intermediate hash maps - we create hash maps when doing join processing, and these maps can end up being large when we are joining a very large number of rows. The hash maps are implemented as standard Java hash maps which are not memory efficient and have a limit of 2B entries, which will be a problem for queries on SF1000. We need to have a more efficient hash map which has no memory limitations We need to assess the impact of this now that we have MemSQL and RapidsSE.
JeroMQ Connection pooling | R2.1 | R2.1
Support for N-way joins | R2.1 | R2.1
Support for CROSS JOIN | R2.1 | R2.1
Optimizer Phase 1: Basic sub-queries | R2.1 | R2.1
Support for dynamic schema (VoltDB 5.0) | R2.1 | R2.1
Literal projection | R2.1 | R2.1
SELECT expressions | R2.1 | R2.1
SELECT DISTINCT | R2.1 | R2.1
Sub-query expressions | R2.1 | R2.1
Support for BETWEEN, IN, HAVING, CASE, COALESCE | R2.1 | R2.1
BLOOM JOINs | R2.2 | R2.1
Support for LIKE | R2.2 | R2.1
Support for SUBSTRING and TRIM |  | R2.1
Support for EXISTS | R2.2 | R2.2
Support for VoltDB 6.0 |  | R2.2
Streaming (Alpha version) |  | R2.2
FULL OUTER JOIN | R2.3 | R2.2
Optimizer Phase 2 (for China Tobacco)
Sub-queries |  | R2.4
Query Caching |  |  | Deferred | PERFORMANCE: This is important for queries where there are repeated sub-queries, which is commonly seen with the "WITH" clause, so that the sub-query is only evaluated once. Some of the SZSE queries used repeated "WITH" clauses. Also, will be important for R (for iterative processing).
Join Order |  |  | Deferred | PERFORMANCE: The peformance of multi-table joins can be signficantly impacted by the ordering of the joins in the final query execution plan. While a sophisticated end-user can provide an optimal odering for the original query, this is can be very difficult for the end-user and should be handled by the query optimizer. To do this requires some form of plan costing in the Optimizer.
Resource Management Framework | R2.3 |  | Deferred | CONCURRENCY/ENTERPRISE READY: We currently have no effective way of limiting the use of system resources, such as file descriptors or memory. This can lead to resource exhaustion, which can cause the DQS to fail. The only mechanism we have today to control this is by limiting the number of concurrent queries that the system will attempt to execute, but even this can fail when pulling up large amounts of data into the Rapids Execution Engine (eg when joining across Connectors).
SQL Windowing - should be called Analytic Windowing | R2.3 |  | Deferred | COMPETITIVE: This is commonly used by customers who want to perform higher order anlytics against SQL data. Some of the TPC-DS queries make use of analytic windowing.
Suport for Third Party Connectors | R2.4 | R2.4 | Part of the Federation Framework
HDFS csv | R2.4 | 2016-11-30
Support for INTERSECT, EXCEPT | R2.4 | R2.4
Support for ROUND | R2.4 | R2.4
Support for STDDEV | R2.4 | R2.4
Suport for WITH | R2.4 |  | Deferred | COMPETITIVE: WITH is commonly used with complex queries as a way to both simplify the final query and to build common table expressions
Support for VIEWs |  |  | Deferred | COMPETITIVE: VIEWs are commonly used in other databases and as such we should be able to support them.
Federations support |  | R2.4
Dynamic Connector configuration |  | R2.4
Support for MemSQL |  | R2.4
System Metadata tables |  | R2.4
RapidsDB manager |  | R2.4
Standardized support for PRECISION |  | R2.4
INTERVAL Artihmetic |  | R2.4
IF, IFNULL, NULLIF, LTRIM and RTRIM |  | R2.4
POWER |  | R2.4
SQL Map-Reduce | R2.5 |  | Out-plan
Scaling 100+ Nodes | R2.5
HARDENING
Partition-centric JOINS |  | R2.1
Off-Heap |  |  |  | See item 4 above
JeroMQ Connection Pooling |  | R2.4
Bloom Filter |  | R2.1
PBJ Improvement |  |  | No longer needed as we have Bloom Join and Nested Join which are sufficient
Resource Manaement Framework |  |  | Deferred | See item 28 above
Co-existance with other systems |  | Out-plan | With Connectors can now isolate other systems if needed. Marked as out-plan pending evidence that raises the priority.

## Stage 3 Rel Plan Reconciliatio
Feature | Planned Release | Actual Release | Comments
JDBC Driver | Q4 | 2016-12-31
Performance
MemSQL | R2.4 | R2.4
Sub-Query | R2.4 | R2.4
Join Order | R2.4 |  | See SOW-Hardening Reconciliation
Query Caching | R2.4 |  | See SOW-Hardening Reconciliation
Non-updatable materialized views
SELECT INTO | 2016-08-01 | 2016-11-30
CREATE MAT VIEW | TBD |  | Out-plan
DDL/DML pass-through
Enterprise Ready
RapidsDB Manager | R2.4 | R2.4
Dynamic System Reconfig | R2.4 | R2.4 | For Connectors
Parallel Loader |  |  | Field Development
Improve SQL Compliance
Date/time arithmetic | R2.4 | R2.4
WITH | R2.4 | TBD | See SOW-Hardening Reconciliation
Analytic Windowing | 2016-09-01 |  | See SOW-Hardening Reconciliation
IFNULL | R2.4 | R2.4
Streaming
INTO <pipe> SELECT (rapids-shell) | R2.4 | R2.4
INTO … SELECT (from RapidsDB) | 2016-09-01 | 2016-11-30
HDFS csv Connector - integration with Federation | 2016-08-01 | 2016-11-30
DDL/DML Support | Q4 |  | Original plan was using some form of pass-through, but is now being implemented as native DDL/DML in RapidsDB
CREATE/DROP TABLE |  | 2016-11-30
INSERT, INSERT … SELECT |  | 2016-11-30
UPDATE |  |  | Deferred
DELETE |  |  | Deferred

## TPC-DS
TPC-DS Query | Oracle Query | Release 2.1 | Release 2.2 | Release 2.3 | Release 2.4 | Release 3.0
Query 1 | Query 12 |  |  |  |  | WITH not supported until 3.0
Query 2 | Query 84 |  |  |  | ROUND not supported until 2.4
Query 3 | Query 45 | fully supported
Query 4 | Query 93 |  |  |  |  | WITH not supported until 3.0
Query 5 | Query 98 | Rollup will not be supported |  |  |  |  | 1
Query 6 | Query 58 | Fully supported
Query 7 | Query 2 | fully supported
Query 8 | Query 63 |  |  |  | INTERSECT not supported until 2.4
Query 9 | Query 49 | fully supported
Query 10 | Query 26 |  | EXISTS not supported until 2.2
Query 11 | Query 51 |  |  |  |  | WITH not supported until 3.0
Query 12 | Query 64 | OVER(PARTITION BY …) not supported |  |  |  |  | 1
Query 13 | Query 91 | fully supported
Query 14 | Query 69 | Rollup will not be supported |  |  | INTERSECT not supported until 2.4 |  | 1
Query 15 | Query 57 | fully supported
Query 16 | Query 25 |  | EXISTS not supported until 2.2
Query 17 | Query 41 |  |  |  | STDDEV_SAMP not supported until 2.4
Query 18 | Query 90 | Rollup will not be supported |  |  |  |  | 1
Query 19 | Query 8 | fully supported
Query 20 | Query 65 | OVER(PARTITION BY …) not supported |  |  |  |  | 1
Query 21 | Query 14 | Rollup will not be supported |  |  |  |  | 1
Query 22 | Query 55 | Rollup will not be supported |  |  |  |  | 1
Query 23 | Query 68 |  |  |  |  | WITH not supported until 3.0
Query 24 | Query 92 |  |  |  |  | WITH not supported until 3.0
Query 25 | Query 9 |  |  |  | STDDEV_SAMP not supported until 2.4
Query 26 | Query 85 | fully supported
Query 27 | Query 16 | Rollup will not be supported |  |  |  |  | 1
Query 28 | Query 36 | fully supported
Query 29 | Query 53 |  |  |  | STDDEV_SAMP not supported until 2.4
Query 30 | Query 75 |  |  |  |  | WITH not supported until 3.0
Query 31 | Query 50 | fully supported |  |  |  | WITH not supported until 3.0
Query 32 | Query 7 |  |  |  | Date arithmetic supported in R2.4 |  | 1
Query 33 | Query 22 |  |  |  |  | WITH not supported until 3.0
Query 34 | Query 73 | fully supported
Query 35 | Query 47 |  | EXISTS not supported until 2.2 |  | STDDEV_SAMP not supported until 2.4
Query 36 | Query 21 | Rollup will not be supported |  |  |  |  | 1
Query 37 | Query 31 |  |  |  | Date arithmetic
Query 38 | Query 54 |  |  |  | INTERSECT not supported until 2.4
Query 39 | Query 5 |  |  |  | STDDEV_SAMP not supported until 2.4
Query 40 | Query 86 |  |  |  | Date arithmetic
Query 41 | Query 62 | fully supported
Query 42 | Query 61 | OVER(PARTITION BY …) not supported |  |  |  |  | 1
Query 43 | Query 15 | fully supported
Query 44 | Query 4 | RANK() OVER() not supported |  |  |  |  | 1
Query 45 | Query 18 | fully supported
Query 46 | Query 23 | fully supported
Query 47 | Query 42 | OVER(PARTITION BY …) not supported |  |  |  |  | 1
Query 48 | Query 74 | fully supported
Query 49 | Query 48 | RANK() OVER() not supported |  |  |  |  | 1
Query 50 | Query 60 | fully supported
Query 51 | Query 46 | OVER(PARTITION BY …) not supported
Query 52 | Query 59 | fully supported
Query 53 | Query 88 | OVER(PARTITION BY …) not supported |  |  |  |  | 1
Query 54 | Query 81 |  |  |  |  | WITH not supported until 3.0
Query 55 | Query 82 | fully supported
Query 56 | Query 83 |  |  |  |  | WITH not supported until 3.0
Query 57 | Query 70 | OVER(PARTITION BY …) not supported |  |  |  |  | 1
Query 58 | Query 19 |  |  |  |  | WITH not supported until 3.0
Query 59 | Query 30 |  |  |  |  | WITH not supported until 3.0
Query 60 | Query 29 |  |  |  |  | WITH not supported until 3.0
Query 61 | Query 97 | fully supported
Query 62 | Query 24 | fully supported
Query 63 | Query 27 | OVER(PARTITION BY …) not supported |  |  |  |  | 1
Query 64 | Query 20 |  |  |  |  | WITH not supported until 3.0
Query 65 | Query 71 | fully supported
Query 66 | Query 39 | fully supported
Query 67 | Query 35 | Rollup will not be supported |  |  |  |  | 1
Query 68 | Query 95 | fully supported
Query 69 | Query 28 |  | EXISTS not supported until 2.2
Query 70 | Query 34 | Rollup will not be supported |  |  |  |  | 1
Query 71 | Query 72 | fully supported
Query 72 | Query 87 | fully supported
Query 73 | Query 79 | fully supported
Query 74 | Query 76 |  |  |  |  | WITH not supported until 3.0
Query 75 | Query 3 |  |  |  |  | WITH not supported until 3.0
Query 76 | Query 99 | fully supported
Query 77 | Query 78 | Rollup will not be supported |  |  |  |  | 1
Query 78 | Query 10 |  |  |  | ROUND not supported until 2.4
Query 79 | Query 89 | fully supported
Query 80 | Query 6 | Rollup will not be supported |  |  |  |  | 1
Query 81 | Query 37 |  |  |  |  | WITH not supported until 3.0
Query 82 | Query 67 |  |  |  | DATE arithmetic
Query 83 | Query 96 |  |  |  |  | WITH not supported until 3.0
Query 84 | Query 80 | fully supported
Query 85 | Query 33 | fully supported
Query 86 | Query 11 | Rollup will not be supported |  |  |  |  | 1
Query 87 | Query 77 |  |  |  | EXCEPT not supported until 2.4
Query 88 | Query 66 | fully supported
Query 89 | Query 56 | OVER(PARTITION BY …) not supported |  |  |  |  | 1
Query 90 | Query 40 | Fully supported
Query 91 | Query 13 | Fully supported
Query 92 | Query 44 |  |  |  |  | WITH not supported until 3.0
Query 93 | Query 52 | fully supported
Query 94 | Query 17 |  | EXISTS not supported until 2.2 |  | Date arithmetic
Query 95 | Query 43 |  |  |  |  | WITH not supported until 3.0
Query 96 | Query 1 | fully supported
Query 97 | Query 38 |  |  |  |  | WITH not supported until 3.0
Query 98 | Query 32 | OVER(PARTITION BY …) not support |  |  |  |  | 1
Query 99 | Query 94 | fully supported
24