## Task List
[8 empty] | Rich |  | Other
Section | Item(s) | Initial Estimate | Actual | Est. Remaining |  | Actual | Est. Remaining | Actual | Est. Remaining | Actual | Est. Remaining
Rich
Craig
Core team (timestamp/interval related)
Core team
Connector specific (Myvan)
Substrate
| Library scan/load | 5 | 4 | (done) |  |  |  | 5 | (done)
| Type framework | 5 | 4 | 1 |  | 5 | 3 | 9 | (done)
| Type/op annotation | 4 | 3 | (done) |  | 3 | 3 | 7 | (done)
| Proc generation | 10 | 7 | 1 |  | 9 | 2 | 12 | (done)
| Misc reorg | 8 | 3 | 5 |  | 9 | 5 | 20 | 4
Query Planner
| Case sensitive IDs & nonreserved words | 2 |  | 2 |  |  |  | 2 | 1
| Op/UDF grammar | 2 | 1 | 1 |  |  |  |  | 1
| Op/UDF generation | 3 | 2 | 1 |  |  |  | 3 | (done)
| Type resolution | 3 | 2 | 1 |  |  |  | 3 | 1
| Object/UDT grammar | 4 |  | (defer) |  |  |  |  | (defer)
| Object/UDT generation | 3 |  | (defer) |  |  |  |  | (defer)
| Array/row grammar | 4 |  | (defer) |  |  |  |  | (defer)
| Array/row generation | 2 |  | (defer) |  |  |  |  | (defer)
| CSE / cache-point marking | 4 |  | 4 |  |  |  |  | (defer)
| CREATE TABLE & CAST grammar changes | [7 empty] | 2
| CREATE TABLE gen | [6 empty] | 1 | 2
| Intervals design & grammar changes | [7 empty] | 1
| Aggregate issues (SUM/COUNT, DISTINCT, discrete) | [7 empty] | 1
| Misc: CAST, ISNULL, IF, COALESCE, DECODE | [7 empty] | 1
Executor Framework
| Distributed Stream | 3 | 3 | 1 |  | 5 | 1 | 5 | 1
| Distributed RunContext | 2 | 2 | 2 |  |  |  | 3 | 1
| Query state/metrics framework | 3 | 1 | 2 |  | 5 | 1 | 7 | 1
| Query state/metrics distribution | 2 | 1 | 2 |  |  |  | 1 | ?
| Query state/metrics retrieval | 4 |  | 4 |  | ? | ? | ? | ?
| EXPLAIN/STATS | 4 |  | 4 |  | ? | ? | ? | ?
| Query hold/cancel/prioritize | 4 |  | (defer) |  |  |  |  | (defer)
| Legacy input adapter | 4 | 4 | 2 |  |  |  | 5 | (done)
| Legacy output adapter | 4 | 4 | 2 |  |  |  | 2 | (done)
| Materialization | 2 | 2 | 2 |  |  |  | 3 | (done)
| Insert | 4 |  | 4 |  |  |  | 1 | 1
| Caching strategy | 4 |  | 4 |  |  |  |  | (defer)
| Caching engine | 5 |  | 5 |  |  |  |  | (defer)
| Query restart | 10 |  | (defer) |  | 1 | (defer) | 1 | (defer)
| Resource tracking framework | 6 | 2 | (defer) |  |  |  | 2 | (defer) ???
| Query/resource scheduler | 10 |  | (defer) |  |  |  |  | (defer) ???
| Exception / Error / Internationalization rework | [6 empty] | 1 | 2
| Column/roster rework | [6 empty] | 5 | 2
| Fed: context portability rework | [6 empty] | 1 | 2
| Fed: general rework | [6 empty] | 1 | (defer)
| Fed: connector API rework | [7 empty] | (defer)
| Fed: caching rework | [7 empty] | (defer)
Connectors
| Update result & context handling | [7 empty] | ?
| Update expr handling | [7 empty] | ?
Query Ops
| Filter | 2 | 1 | (done) |  |  |  |  | (done)
| Project | 3 | 1 | (done) |  |  |  | 2 | (done)
| Aggregate | 5 | 2 | 3 |  | 7 | 2 | 9 | 2
| Join | 7 |  | 7 |  |  |  | 3 | 4
| Union / Intersect / Except | 5 |  | 5 |  |  |  |  | 5
| Order | 5 |  | 5 |  |  |  |  | 5
| Partitioning/co-partitioning rework | [7 empty] | 2
Expr Ops
| Literal vs constant vs invariant review | [7 empty] | 1
| Normalization review / rework | [7 empty] | 1
| Boolean simplification review / rework | [7 empty] | 2
| Range preds review (executable expr? ) | [7 empty] | 2
FastBoolean | < <= = <> >= > | 1 | 1 | (done) |  |  |  |  | (done)
| And / Or / Not / IsNull | 1 | 1 | (done) |  |  |  |  | (done)
| If | 1 |  | 1 |  |  |  |  | (done)
FastInteger | Frame / casts / conversions | 2 | 1 | (done) |  | 1 | 1 | 1 | (done)
| < <= = <> >= > IsNull | 1 | 1 | (done) |  |  |  |  | (done)
| + - * / | 1 | 1 | (done) |  |  |  |  | (done)
| Abs, Ceiling, Floor, Mod | 1 |  | 1 |  |  |  |  | (done)
| Round | 1 |  | 1 | [6 empty] | 1
| Count, Min, Max | 1 |  | 1 |  |  |  | 1 | (done)
| Sum, Avg | 1 |  | 1 | 4 |  |  |  | (done)
Int64 JavaLong | Frame / casts / conversions | 2 | [6 empty] | (done)
| < <= = <> >= > IsNull | 1 | [6 empty] | (done)
| + - * / | 1 | [6 empty] | (done)
| Abs, Ceiling, Floor, Mod | 1 | [6 empty] | (done)
| Round | 1
| Count, Min, Max | 1 | [6 empty] | (done)
| Sum, Avg | 1 |  |  |  | 1 | 1 |  | (done)
FastDecimal | Frame / casts / conversions | 2 |  | 2 |  |  |  |  | (done)
| < <= = <> >= > IsNull | 2 |  | 2 | [6 empty] | 2
| + - * / | 2 |  | 2 | [6 empty] | 2
| Abs, Ceiling, Floor, Mod, Exp, Pow, Sqrt | 2 |  | 2 | [6 empty] | 2
| Round | 2 |  | 2 | [6 empty] | 2
| Count, Min, Max | 1 |  | 1 | [6 empty] | 1
| Sum, Avg | 1 |  | 1 | 10 | [5 empty] | 1
BigDecimal | Frame / casts / conversions | 2 |  | 2 |  |  |  |  | (done)
| < <= = <> >= > IsNull | 1 |  | 1 |  |  |  |  | (done)
| + - * / | 1 |  | 1 | [6 empty] | 1
| Abs, Ceiling, Floor, Mod, Exp, Pow, Sqrt | 1 |  | 1 | [6 empty] | 1
| Round | 1 |  | 1 | [6 empty] | 1
| Count, Min, Max | 1 |  | 1 | [6 empty] | 1
| Sum, Avg | 1 |  | 1 | 6 | [5 empty] | 1
FastFloat | Frame / casts / conversions | 2 | 1 | (done) |  |  |  | 1 | (done)
| < <= = <> >= > IsNull | 1 | 1 | (done) |  |  |  | 1 | (done)
| + - * / | 1 |  | 1 |  |  |  |  | (done)
| Abs, Ceiling, Floor, Mod, Exp, Pow, Sqrt | 2 |  | 2
| Round | 1 |  | 1
| Count, Min, Max | 1 |  | 1
| Sum, Avg | 1 |  | 1 | 6
| Variance / VarSamp / StdDev / StdDevSamp | 2 |  | 2 |  |  |  |  | 2
Varchar JavaString | Frame / casts / conversions | 2 |  | 2 |  |  |  |  | (done)
| < <= = <> >= > IsNull | 1 |  | 1 |  |  |  |  | (done)
| Concat, SubString2, SubString3 | 1 |  | 1 | [6 empty] | 1
| Char | 1 |  | 1 | [6 empty] | 1
| CharLength, Position | 1 |  | 1 | [6 empty] | 1
| Left, Right, LTrim, RTrim | 1 |  | 1 | [6 empty] | 1
| Like, LikeEscape | 1 |  | 1 | [6 empty] | 1
| Lower, Upper | 1 |  | 1 |  |  |  |  | (done)
| Count, Min, Max | 1 |  | 1 | 8 | [5 empty] | 1
Varbinary | Frame / casts / conversions | 2 |  | 2 |  |  |  |  | 1
| < <= = <> >= > IsNull | 1 |  | 1 | 1 | [5 empty] | 1
FastTimestamp | Frame / casts / conversions | 2 |  | 2 |  |  |  |  | 1
| < <= = <> >= > IsNull | 1 |  | 1 | [6 empty] | 1
| - Timestamp64 | 1 |  | 1 | [6 empty] | 1
| + - Interval64 | 1 |  | 1 | [6 empty] | 1
| + - OmniInterval | 2 |  | 2 | [6 empty] | 2
| DayOfWeek, DayOfMonth, DayOfYear | 1 |  | 1 | [6 empty] | 1
| Hour, Minute, Second / ExtractSecond | 1 |  | 1 | [6 empty] | 1
| Month, Quarter, Year | 1 |  | 1 | [6 empty] | 1
| WeekDay, WeekOfYear | 1 |  | 1 | [6 empty] | 1
| FromUnixTime | 1 |  | 1 | [6 empty] | 1
| Count, Min, Max | 1 |  | 1 | 11 | [5 empty] | 1
TimeInterval | Frame / casts / conversions | 2 |  | 2 |  |  |  |  | 1
| < <= = <> >= > IsNull | 1 |  | 1 | [6 empty] | 1
| + - * / | 1 |  | 1 | 2 | [5 empty] | 1
OmniInterval | Frame / casts / conversions | 3 |  | 3 |  |  |  |  | 1
| < <= = <> >= > IsNull | 1 |  | 1 | [6 empty] | 1
| + - * / | 1 |  | 1 | 2 | [5 empty] | 1
[8 empty] | Total | 54 |  | 38
|  |  |  | Total | 50

## Key Milestones
2018-06-14 | Complex JOINs - answer the question about JIT Capacity
2018-06-21 | Run full set of TPC-H queries
Dependencies:
String functions: LIKE, SUBSTRING
Timestamp functions: EXTRACT, INTERVAL ( can work around)
Misc functions: BETWEEN (can work around), IN (can work around)
ORDER BY - can do initial run and get results without ordering
2018-06-28 | SE Interface: major issues resolved and plan in place
2018-06-28 | Review and update schedule
2018-07-31 | Code complete